## README
HOW TO UPDATE THE DASHBOARD | طريقة تحديث لوحة المتابعة
1. Each month, after the IPC is issued, add one row in 'Invoices' (copy values from the Payment Log). | ١. كل شهر بعد إصدار المستخلص أضف سطراً في شيت Invoices من سجل الدفعات.
2. In 'Sections' update Previous / Current / Cumulative from the BOQ Summary page of the IPC. | ٢. في شيت Sections حدّث السابق / الحالي / التراكمي من صفحة ملخص الـBOQ في المستخلص.
3. In 'BOQ_Items' update Previous / Current / To-Date quantities (rates & amounts are recalculated if left blank). | ٣. في شيت BOQ_Items حدّث الكميات السابقة / الحالية / التراكمية (المبالغ تُحسب تلقائياً لو تُركت فارغة).
4. In 'Performance' add the P6 update row: Data Date, Planned %, Actual % (physical progress). | ٤. في شيت Performance أضف سطر التحديث من البريمافيرا: تاريخ البيانات، المخطط ٪، الفعلي ٪.
5. 'Baseline_Plan' = monthly planned value (SAR excl. VAT) from the P6 baseline (or import the .xer in the site). | ٥. شيت Baseline_Plan = القيمة المخططة الشهرية من البيز لاين (أو استورد ملف ‎.xer من الموقع مباشرة).
6. Update 'Data Date' in 'Project'. Then open the site → Import File tab → drop this workbook. | ٦. حدّث Data Date في شيت Project، ثم افتح الموقع ← تبويب Import File ← ارفع الملف.
7. To publish for everyone: upload it to GitHub as data/project-data.xlsx (replace the old one). | ٧. للنشر للجميع: ارفعه على GitHub باسم data/project-data.xlsx بدلاً من القديم.
RULES | قواعد
• Do not rename sheets or header cells. Extra columns are ignored. | • لا تغيّر أسماء الشيتات أو العناوين. الأعمدة الإضافية يتم تجاهلها.
• Amounts in SAR. Work done & recovery are EXCLUDING VAT. Dates as real Excel dates. | • المبالغ بالريال. قيمة الأعمال والاسترداد بدون ضريبة. التواريخ بصيغة تاريخ إكسل.
• Percent columns: type 12.5 or 12.5% — both work. | • أعمدة النسب: اكتب 12.5 أو ‎12.5% — الاثنين صحيح.
• Blank VAT / Net Certified are computed from VAT % in 'Project'. | • لو تُركت الضريبة أو الصافي فارغة يتم حسابها تلقائياً.
Yellow cells = inputs you update every month.

## Project
Field | Value | Note
Project Name | Development of Taif Road — Section C
Contract No | 20250928162
Client | Royal Commission for Riyadh City (RCRC)
Consultant | WSP
Contractor | RTCC – IC ICTAS JV
Contract Value (excl VAT) | 1557000000.1
Contract Value (incl VAT) | 1790550000.11
Approved Change Orders (excl VAT) | 0
Advance Payment (incl VAT) | 179055000.01
VAT % | 15
Advance Recovery % | 10
Retention % | 0
Commencement Date | 2025-10-15 | Start of IPC-01 period
Planned Completion Date |  | Fill from contract / P6 baseline (enables Time-elapsed KPI)
Data Date | 2026-08-22 | Usually the 'Period To' of the latest IPC

## Invoices
IPC No | Period From | Period To | Work Done (excl VAT) | Advance Recovery (excl VAT) | VAT | Retention (incl VAT) | Net Certified (incl VAT) | Status | Paid Amount | Paid Date | Remarks
1 | 2025-10-15 | 2026-02-22 | 1409896.37 | 140989.64 | 190336.01 | 0 | 1459242.74 | Certified
2 | 2026-02-23 | 2026-03-22 | 656249.4 | 65624.94 | 88593.67 | 0 | 679218.13 | Certified
3 | 2026-03-23 | 2026-04-22 | 3620445.21 | 362044.52 | 488760.1 | 0 | 3747160.79 | Certified
4 | 2026-04-23 | 2026-05-22 | 4926757.07 | 492675.71 | 665112.2 | 0 | 5099193.57 | Certified
5 | 2026-05-23 | 2026-06-22 | 3099142.08 | 309914.21 | 418384.18 | 0 | 3207612.05 | Certified
6 | 2026-06-23 | 2026-07-22 | 4881764.98 | 488176.5 | 659038.27 | 0 | 5052626.75 | Certified
7 | 2026-07-23 | 2026-08-22 | 33138886.06 | 3313888.61 | 4473749.62 | 0 | 34298747.07 | Submitted

## Sections
Section | Description | Contract Amount | Previous Amount | Current Amount | Cumulative Amount | Planned % To Date
Section 01 | General Items | 0 | 0 | 0 | 0
Section 02 | Earthworks | 90825644.98 | 3086007.57 | 215072.73 | 3301080.3
Section 03 | Base Courses | 47371713.86 | 0 | 0 | 0
Section 04 | Bituminous Works | 171682971.5 | 0 | 0 | 0
Section 05 | Minor Structures, Underpasses & Retaining Walls | 52056078.88 | 0 | 0 | 0
Section 5A | Bridge @ 4+050 | 94018403.04 | 8674314.3 | 17610032.03 | 26284346.33
Section 5B | Bridge @ 7+300 | 93631147.04 | 1974696.69 | 9848160.52 | 11822857.21
Section 5C | Bridge @ 10+550 | 81506724.92 | 0 | 1358425.14 | 1358425.14
Section 5D | Underpass @ 13+500 | 26754465.6 | 0 | 0 | 0
Section 5E | Underpass @ 14+400 | 32793604.4 | 0 | 0 | 0
Section 5F | Bridge @ Jeddah Junction | 41934082.47 | 508801.46 | 764204.07 | 1273005.53
Section 06 | Road Safety Works | 106639613.9 | 0 | 0 | 0
Section 07 | Electrical Works | 290371156.22 | 0 | 1739513.68 | 1739513.68
Section 08 | Landscape | 36719942.93 | 0 | 0 | 0
Section 09 | Traffic Appurtenances | 19257511.58 | 0 | 0 | 0
Section 10 | Wet Utility | 148746136.6 | 4350435.09 | 1603477.89 | 5953912.98
Section 11 | ITS | 24852042.87 | 0 | 0 | 0
Section 12 | Diversion Works | 77221842.65 | 0 | 0 | 0
Section 13A | Pedestrian Bridge 1 | 17256741.2 | 0 | 0 | 0
Section 13B | Pedestrian Bridge 2 | 18275591.85 | 0 | 0 | 0
Section 13C | Pedestrian Bridge 3 | 16062627.03 | 0 | 0 | 0
Section 13D | Pedestrian Bridge 4 | 16055504.47 | 0 | 0 | 0
Section 13E | Pedestrian Bridge 5 | 16076872.15 | 0 | 0 | 0
Section 13F | Pedestrian Bridge 6 | 17256741.2 | 0 | 0 | 0
Section 13G | Pedestrian Bridge 7 | 17256741.2 | 0 | 0 | 0
Section 14 | Traffic Signal | 2376097.56 | 0 | 0 | 0
| Grand Total | 0 | 0 | 0 | 0
Planned % To Date: optional, from P6 (per WBS/section) — draws a planned marker on each progress bar.

## BOQ_Items
Bill | Item No | Description | Unit | Contract Qty | Unit Rate | Contract Amount | Previous Qty | Current Qty | To-Date Qty | Current Amount | To-Date Amount
2 | 2.1.1 | Clearing and Grubbing | Square Meter | 542197.25 | 2.3 | 1247053.68 | 2482.55 | 0 | 2482.55 | 0 | 5709.865
2 | 2.1.2 | Individual tree Removal | Unit | 2726 | 344.55 | 939243.3 | 1162 | 0 | 1162 | 0 | 400367.1
2 | 2.2.1 | Removal and Disposal of Existing traffic Signals | Unit | 28 | 669.97 | 18759.16 | 4 | 0 | 4 | 0 | 2679.88
2 | 2.2.2 | Removal and Disposal of Existing Single Pole Signages | Unit | 821 | 143.57 | 117870.97 | 242 | 0 | 242 | 0 | 34743.94
2 | 2.2.3 | Removal and Disposal of Existing Double Pole Signages | Unit | 49 | 191.42 | 9379.58 | 0 | 0 | 0 | 0 | 0
2 | 2.2.4 | Removal and Disposal of Existing Triple Pole Signages | Unit | 14 | 239.28 | 3349.92 | 0 | 0 | 0 | 0 | 0
2 | 2.2.5 | Removal and Disposal of Existing cantilever Gantry | ton | 55 | 1148.51 | 63168.05 | 4.58 | 0 | 4.58 | 0 | 5260.1758
2 | 2.2.6 | Removal and Disposal of Existing Manholes (All types and sizes) | Unit | 1135 | 669.97 | 760415.95 | 0 | 0 | 0 | 0 | 0
2 | 2.2.7 | Removal and Disposal of Existing Crash Barriers | Linear Metre | 520 | 143.57 | 74656.4 | 0 | 0 | 0 | 0 | 0
2 | 2.2.8 | Removal and Disposal of Existing RCC Box Conduit (1.8m x 1.5m) | Linear Metre | 540 | 114.85 | 62019 | 0 | 0 | 0 | 0 | 0
2 | 2.2.9 | Removal and Disposal of Existing Light poles | Unit | 701 | 516.83 | 362297.83 | 73 | 0 | 73 | 0 | 37728.59
2 | 2.2.10 | Removal and Disposal of Existing Sign post Base | Cubic Metre | 150 | 1339.93 | 200989.5 | 86.9 | 0 | 86.9 | 0 | 116439.917
2 | 2.2.11 | Removal of Signs (Any type) | Square Metre | 1162.79 | 133.99 | 155801.56 | 123.53 | 0 | 123.53 | 0 | 16551.7847
2 | 2.2.12 | Removal and Shifting of Existing Transformers | Unit | 6 | 3445.54 | 20673.24 | 0 | 0 | 0 | 0 | 0
2 | 2.2.13 | Removal and Disposal of Existing Fence | Linear Metre | 3000 | 47.86 | 143580 | 0 | 0 | 0 | 0 | 0
2 | 2.2.14 | Removal and Disposal of Existing Barriers (Bollard type) | Unit | 3456 | 57.43 | 198478.08 | 637 | 90 | 727 | 5168.7 | 41751.61
2 | 2.2.15 | Dismantling of Existing Building | Square Meter | 1521 | 401.98 | 611411.58 | 0 | 0 | 0 | 0 | 0
2 | 2.2.16 | Removal of Curb | Linear Meter | 110000 | 4.59 | 504900 | 57000.2 | 0 | 57000.2 | 0 | 261630.918
2 | 2.2.17 | Removal of Concrete, Paving Tile & Shotcrete Slope Protection | Square Meter | 182000 | 5.75 | 1046500 | 137970.83 | 0 | 137970.83 | 0 | 793332.2725
2 | 2.2.18 | Removal of Bituminous & Granular Pavement upto Subgrade Top Level | Square Meter | 646840 | 11.49 | 7432191.6 | 116402.25 | 18268.41 | 134670.66 | 209904.0309 | 1547365.8834
2 | 2.2.19 | Removal of Planter Box | Unit | 1840 | 95.71 | 176106.4 | 371 | 0 | 371 | 0 | 35508.41
2 | 2.2.20 | Removal Traffic Monitoring Cameras | Unit | 6 | 669.97 | 4019.82 | 3 | 0 | 3 | 0 | 2009.91
2 | 2.3.1 | Roadway Excavation | Cubic Meter | 184183.3 | 56.71 | 10445034.94 | 0 | 0 | 0 | 0 | 0
2 | 2.3.2.1 | Structural Excavation-Other Structures & Underpasses | Cubic Meter | 44989.15 | 69.23 | 3114598.89 | 0 | 0 | 0 | 0 | 0
2 | 2.4.1 | Embankment (From Roadway Cutting) | Cubic Meter | 147346.64 | 62.61 | 9225373.13 | 0 | 0 | 0 | 0 | 0
2 | 2.4.2 | Embankment (From Borrow Areas) | Cubic Meter | 35921.93 | 112.59 | 4044450.01 | 0 | 0 | 0 | 0 | 0
2 | 2.4.3 | Imported Fill for MSE Wall | Cubic Meter | 85640.31 | 124.43 | 10656223.62 | 0 | 0 | 0 | 0 | 0
2 | 2.5.1 | Subgrade, Depth 300mm | Square Meter | 468483.09 | 23.43 | 10976558.76 | 0 | 0 | 0 | 0 | 0
2 | 2.5.2 | Subgrade Preparation | Square Meter | 646840 | 19.78 | 12794495.2 | 0 | 0 | 0 | 0 | 0
2 | 2.6.1 | CLSM Material as approved by Engineer | Cubic Meter | 10000 | 398.86 | 3988600 | 0 | 0 | 0 | 0 | 0
2 | 2.6.2 | CLSM with Fly Ash | Cubic Meter | 3000 | 498.58 | 1495740 | 0 | 0 | 0 | 0 | 0
2 | 2.7 | Geogrid as approved by Engineer and utilised | Linear Meter | 7000 | 119.66 | 837620 | 0 | 0 | 0 | 0 | 0
2 | 2.8 | Horizontal Direct Drilling for crossing existing Road | Linear Meter | 240 | 37892.02 | 9094084.8 | 0 | 0 | 0 | 0 | 0
5A | 5A.1.1.1 | Structural Excavation including Backfilling | Cubic Meter | 9800 | 107.64 | 1054872 | 3364.83 | 1700.6 | 5065.43 | 183052.584 | 545242.8852
5A | 5A.2.1 | Structural Concrete for Bridge Substructure, Class B (40 Mpa) | Cubic Meter | 7000 | 1273.98 | 8917860 | 2878.48 | 798.12 | 3676.6 | 1016788.9176 | 4683914.868
5A | 5A.2.2 | Structural Concrete for Bridge Substructure, Class C (45 Mpa) | Cubic Meter | 720 | 2323.33 | 1672797.6 | 386 | 317.92 | 703.92 | 738633.0736 | 1635438.4536
5A | 5A.2.3 | Blinding Concrete Work Under foundation and approach slabs 100mm | Square Meter | 3300 | 95.53 | 315249 | 1517.51 | 228.3 | 1745.81 | 21809.499 | 166777.2293
5A | 5A.3.1 | Bearing Devices, Pot, Sliding, 2000 Ton | Unit | 18 | 69676.45 | 1254176.1 | 0 | 3.7 | 3.7 | 257802.865 | 257802.865
5A | 5A.4.1 | Bearing Devices, Pot, Guided, 2000 Ton | Unit | 18 | 82235.34 | 1480236.12 | 0 | 3.7 | 3.7 | 304270.758 | 304270.758
5A | 5A.5 | Prestressing Steel | Ton | 380 | 26212.72 | 9960833.6 | 0 | 206.27 | 206.27 | 5406897.7544 | 5406897.7544
5A | 5A.6 | Cast-in-Place Prestressed Concrete Structural Members, Class D (50 Mpa) | Cubic Meter | 10250 | 3430.29 | 35160472.5 | 0 | 1930.07 | 1930.07 | 6620699.8203 | 6620699.8203
5A | 5A.7.1 | Expansion Joints, Less than 50mm with Backing rod and sealant | Linear Meter | 72 | 170.86 | 12301.92 | 0 | 0 | 0 | 0 | 0
5A | 5A.7.2 | Expansion Joints, greater than 75 mm | Linear Meter | 145 | 7881.45 | 1142810.25 | 0 | 0 | 0 | 0 | 0
5A | 5A.8.1 | Bridge single face parapet | Linear Meter | 1570 | 1350.32 | 2120002.4 | 0 | 0 | 0 | 0 | 0
5A | 5A.9 | Heavy duty Gully Grates and Frames | Units | 38 | 1175.79 | 44815.24 | 0 | 0 | 0 | 0 | 0
5A | 5A.10 | Permeable Material behind Abutment with 300mm thick | Square Metre | 550 | 55.56 | 30558 | 0 | 0 | 0 | 0 | 0
5A | 5A.11 | Granular Backfill Behind Abutment | Cubic Metre | 1700 | 104.66 | 177922 | 0 | 0 | 0 | 0 | 0
5A | 5A.12.1 | Bridge Deck Drainage System (150mm dia UPVC) | Linear Meter | 430 | 466.64 | 200655.2 | 0 | 0 | 0 | 0 | 0
5A | 5A.12.2 | Bridge Deck Drainage System (150mm dia Perforated PVC) | Linear Meter | 197 | 720.17 | 141873.49 | 0 | 0 | 0 | 0 | 0
5A | 5A.12.3 | Bridge Deck Drainage System - Flexible Drainage Pipe 75 mm dia | Linear Meter | 100 | 341.71 | 34205.17 | 0 | 0 | 0 | 0 | 0
5A | 5A.12.4 | Bridge Deck Drainage System (75mm Dia PVC Pipe) | Linear Meter | 18 | 275.58 | 5015.56 | 0 | 0 | 0 | 0 | 0
5A | 5A.12.5 | Bridge Deck Drainage System (150mm dia Imperforated PVC) | Linear Meter | 80 | 846.93 | 67754.4 | 0 | 0 | 0 | 0 | 0
5A | 5A.13.1 | Waterproof Membrane, 2 Layers | Square Meter | 5100 | 155.15 | 791265 | 3699.94 | 463.73 | 4163.67 | 71947.7095 | 645993.4005
5A | 5A.13.2 | Waterproof Membrane For Bridge Deck (Pitchmastic) | Square Meter | 14400 | 179.95 | 2591280 | 0 | 0 | 0 | 0 | 0
5A | 5A.13.3 | Polythene Membrane For Approach Slab, 2 Layers (150 micron) | Square Meter | 400 | 59.27 | 23708 | 0 | 0 | 0 | 0 | 0
5A | 5A.13.4 | Bituminous Painting for Buried Concrete | Square Meter | 2830 | 81.31 | 230107.3 | 0 | 0 | 0 | 0 | 0
5A | 5A.14.1 | Protective Coating for Concrete Structure, Resistance to Weathering | Square Meter | 21800 | 143.96 | 3138328 | 0 | 0 | 0 | 0 | 0
5A | 5A.15 | Reinforcing Steel, Grade 60 | Kilogram | 3850000 | 5.68 | 21868000 | 533306.2 | 526079.06 | 1059385.26 | 2988129.0608 | 6017308.2768
5A | 5A.16 | Furnishing and Installing Heavy Duty gates in Inspection Chamber | Unit | 108 | 4703.15 | 507940.2 | 0 | 0 | 0 | 0 | 0
5A | 5A.17.1 | Bituminous Concrete Wearing Course for Bridge Section, Depth 70mm | Square Meter | 13800 | 77.78 | 1073364 | 0 | 0 | 0 | 0 | 0
5B | 5B.1.1.1 | Structural Excavation including Backfilling | Cubic Meter | 9800 | 107.64 | 1054872 | 1083.58 | 2458.09 | 3541.67 | 264588.8076 | 381225.3588
5B | 5B.2.1 | Structural Concrete for Bridge Substructure, Class B (40 Mpa) | Cubic Meter | 6775 | 1273.98 | 8631214.5 | 647.5 | 1378.5 | 2026 | 1756181.43 | 2581083.48
5B | 5B.2.2 | Structural Concrete for Bridge Substructure, Class C (45 Mpa) | Cubic Meter | 670 | 2323.33 | 1556631.1 | 47.08 | 143.15 | 190.23 | 332584.6895 | 441967.0659
5B | 5B.2.3 | Blinding Concrete Work Under foundation and approach slabs 100mm | Square Meter | 3300 | 95.53 | 315249 | 491.54 | 801.5 | 1293.04 | 76567.295 | 123524.1112
5B | 5B.3.1 | Bearing Devices, Pot, Sliding, 2000 Ton | Unit | 18 | 69676.45 | 1254176.1 | 0 | 0 | 0 | 0 | 0
5B | 5B.4.1 | Bearing Devices, Pot, Guided, 2000 Ton | Unit | 18 | 82235.34 | 1480236.12 | 0 | 0 | 0 | 0 | 0
5B | 5B.5 | Prestressing Steel | Ton | 380 | 26212.72 | 9960833.6 | 0 | 0 | 0 | 0 | 0
5B | 5B.6 | Cast-in-Place Prestressed Concrete Structural Members, Class D (50 Mpa) | Cubic Meter | 10250 | 3430.29 | 35160472.5 | 0 | 1100.59 | 1100.59 | 3775342.8711 | 3775342.8711
5B | 5B.7.1 | Expansion Joints, Less than 50mm with Backing rod and sealant | Linear Meter | 72 | 170.86 | 12301.92 | 0 | 0 | 0 | 0 | 0
5B | 5B.7.2 | Expansion Joints, greater than 75 mm | Linear Meter | 145 | 7881.45 | 1142810.25 | 0 | 0 | 0 | 0 | 0
5B | 5B.8.1 | Bridge single face parapet | Linear Meter | 1570 | 1350.32 | 2120002.4 | 0 | 0 | 0 | 0 | 0
5B | 5B.9 | Heavy duty Gully Grates and Frames | Units | 38 | 1175.79 | 44815.24 | 0 | 0 | 0 | 0 | 0
5B | 5B.10 | Permeable Material behind Abutment with 300mm thick | Square Metre | 550 | 55.56 | 30558 | 0 | 0 | 0 | 0 | 0
5B | 5B.11 | Granular Backfill Behind Abutment | Cubic Metre | 1700 | 104.66 | 177922 | 0 | 0 | 0 | 0 | 0
5B | 5B.12.1 | Bridge Deck Drainage System (150mm dia UPVC) | Linear Meter | 430 | 466.64 | 200655.2 | 0 | 0 | 0 | 0 | 0
5B | 5B.12.2 | Bridge Deck Drainage System (150mm dia Perforated PVC) | Linear Meter | 197 | 720.17 | 141873.49 | 0 | 0 | 0 | 0 | 0
5B | 5B.12.3 | Bridge Deck Drainage System - Flexible Drainage Pipe 75 mm dia | Linear Meter | 100 | 341.71 | 34205.17 | 0 | 0 | 0 | 0 | 0
5B | 5B.12.4 | Bridge Deck Drainage System (75mm Dia PVC Pipe) | Linear Meter | 18 | 275.58 | 5015.56 | 0 | 0 | 0 | 0 | 0
5B | 5B.12.5 | Bridge Deck Drainage System (150mm dia Imperforated PVC) | Linear Meter | 80 | 846.93 | 67754.4 | 0 | 0 | 0 | 0 | 0
5B | 5B.13.1 | Waterproof Membrane, 2 Layers | Square Meter | 5100 | 155.15 | 791265 | 804 | 1072.72 | 1876.72 | 166432.508 | 291173.108
5B | 5B.13.2 | Waterproof Membrane For Bridge Deck (Pitchmastic) | Square Meter | 14400 | 179.95 | 2591280 | 0 | 0 | 0 | 0 | 0
5B | 5B.13.3 | Polythene Membrane For Approach Slab, 2 Layers (150 micron) | Square Meter | 400 | 59.27 | 23708 | 0 | 0 | 0 | 0 | 0
5B | 5B.13.4 | Bituminous Painting for Buried Concrete | Square Meter | 2830 | 81.31 | 230107.3 | 0 | 0 | 0 | 0 | 0
5B | 5B.14.1 | Protective Coating for Concrete Structure, Resistance to Weathering | Square Meter | 21800 | 143.96 | 3138328 | 0 | 0 | 0 | 0 | 0
5B | 5B.15 | Reinforcing Steel, Grade 60 | Kilogram | 3850000 | 5.68 | 21868000 | 132408.15 | 612053.33 | 744461.48 | 3476462.9144 | 4228541.2064
5B | 5B.16 | Furnishing and Installing Heavy Duty gates in Inspection Chamber | Unit | 108 | 4703.15 | 507940.2 | 0 | 0 | 0 | 0 | 0
5B | 5B.17.1 | Bituminous Concrete Wearing Course for Bridge Section, Depth 70mm | Square Meter | 14000 | 77.78 | 1088920 | 0 | 0 | 0 | 0 | 0
5C | 5C.1.1.1 | Structural Excavation including Backfilling | Cubic Meter | 8000 | 107.64 | 861120 | 0 | 866.97 | 866.97 | 93320.6508 | 93320.6508
5C | 5C.2.1 | Structural Concrete for Bridge Substructure, Class B (40 Mpa) | Cubic Meter | 6000 | 1273.98 | 7643880 | 0 | 552 | 552 | 703236.96 | 703236.96
5C | 5C.2.2 | Structural Concrete for Bridge Substructure, Class C (45 Mpa) | Cubic Meter | 560 | 2323.33 | 1301064.8 | 0 | 0 | 0 | 0 | 0
5C | 5C.2.3 | Blinding Concrete Work Under foundation and approach slabs 100mm | Square Meter | 2750 | 95.53 | 262707.5 | 0 | 394.45 | 394.45 | 37681.8085 | 37681.8085
5C | 5C.3.1 | Bearing Devices, Pot, Sliding, 2000 Ton | Unit | 14 | 69676.45 | 975470.3 | 0 | 0 | 0 | 0 | 0
5C | 5C.4.1 | Bearing Devices, Pot, Guided, 2000 Ton | Unit | 14 | 82235.34 | 1151294.76 | 0 | 0 | 0 | 0 | 0
5C | 5C.5 | Prestressing Steel | Ton | 320 | 26212.72 | 8388070.4 | 0 | 0 | 0 | 0 | 0
5C | 5C.6 | Cast-in-Place Prestressed Concrete Structural Members, Class D (50 Mpa) | Cubic Meter | 9200 | 3430.29 | 31558668 | 0 | 0 | 0 | 0 | 0
5C | 5C.7.1 | Expansion Joints, Less than 50mm with Backing rod and sealant | Linear Meter | 72 | 170.86 | 12301.92 | 0 | 0 | 0 | 0 | 0
5C | 5C.7.2 | Expansion Joints, greater than 75 mm | Linear Meter | 145 | 7881.45 | 1142810.25 | 0 | 0 | 0 | 0 | 0
5C | 5C.8.1 | Bridge single face parapet | Linear Meter | 1280 | 1350.32 | 1728409.6 | 0 | 0 | 0 | 0 | 0
5C | 5C.9 | Heavy duty Gully Grates and Frames | Units | 32 | 1175.79 | 37760.5 | 0 | 0 | 0 | 0 | 0
5C | 5C.10 | Permeable Material behind Abutment with 300mm thick | Square Metre | 550 | 55.56 | 30558 | 0 | 0 | 0 | 0 | 0
5C | 5C.11 | Granular Backfill Behind Abutment | Cubic Metre | 1700 | 104.66 | 177922 | 0 | 0 | 0 | 0 | 0
5C | 5C.12.1 | Bridge Deck Drainage System (150mm dia UPVC) | Linear Meter | 350 | 466.64 | 163324 | 0 | 0 | 0 | 0 | 0
5C | 5C.12.2 | Bridge Deck Drainage System (150mm dia Perforated PVC) | Linear Meter | 197 | 720.17 | 141873.49 | 0 | 0 | 0 | 0 | 0
5C | 5C.12.3 | Bridge Deck Drainage System - Flexible Drainage Pipe 75 mm dia | Linear Meter | 77 | 341.71 | 26386.85 | 0 | 0 | 0 | 0 | 0
5C | 5C.12.4 | Bridge Deck Drainage System (75mm Dia PVC Pipe) | Linear Meter | 18 | 275.58 | 5015.56 | 0 | 0 | 0 | 0 | 0
5C | 5C.12.5 | Bridge Deck Drainage System (150mm dia Imperforated PVC) | Linear Meter | 80 | 846.93 | 67754.4 | 0 | 0 | 0 | 0 | 0
5C | 5C.13.1 | Waterproof Membrane, 2 Layers | Square Meter | 4300 | 155.15 | 667145 | 0 | 556 | 556 | 86263.4 | 86263.4
5C | 5C.13.2 | Waterproof Membrane For Bridge Deck (Pitchmastic) | Square Meter | 11800 | 179.95 | 2123410 | 0 | 0 | 0 | 0 | 0
5C | 5C.13.3 | Polythene Membrane For Approach Slab, 2 Layers (150 micron) | Square Meter | 400 | 59.27 | 23708 | 0 | 0 | 0 | 0 | 0
5C | 5C.13.4 | Bituminous Painting for Buried Concrete | Square Meter | 2300 | 81.31 | 187013 | 0 | 0 | 0 | 0 | 0
5C | 5C.14.1 | Protective Coating for Concrete Structure, Resistance to Weathering | Square Meter | 17500 | 143.96 | 2519300 | 0 | 0 | 0 | 0 | 0
5C | 5C.15 | Reinforcing Steel, Grade 60 | Kilogram | 3350000 | 5.68 | 19028000 | 0 | 77099 | 77099 | 437922.32 | 437922.32
5C | 5C.16 | Furnishing and Installing Heavy Duty gates in Inspection Chamber | Unit | 84 | 4703.15 | 395064.6 | 0 | 0 | 0 | 0 | 0
5C | 5C.17.1 | Bituminous Concrete Wearing Course for Bridge Section, Depth 70mm | Square Meter | 11400 | 77.78 | 886692 | 0 | 0 | 0 | 0 | 0
5F | 5F.1.1.1 | Structural Excavation including Backfilling | Cubic Meter | 2500 | 107.64 | 269100 | 469.49 | 0 | 469.49 | 0 | 50535.9036
5F | 5F.2.1 | Structural Concrete for Bridge Substructure, Class B (40 Mpa) | Cubic Meter | 1600 | 1351.68 | 2162688 | 196.88 | 245.64 | 442.52 | 332026.6752 | 598145.4336
5F | 5F.2.2 | Structural Concrete for Bridge Substructure, Class C (45 Mpa) | Cubic Meter | 500 | 3371.3 | 1685650 | 0 | 45.89 | 45.89 | 154708.957 | 154708.957
5F | 5F.2.3 | Blinding Concrete Work Under foundation and approach slabs 100mm | Square Meter | 100 | 95.53 | 9553 | 100 | 0 | 100 | 0 | 9553
5F | 5F.3.1 | Structural Concrete for Bridge Superstructure, Class D (50 Mpa) | Cubic Meter | 1100 | 4203.44 | 4623784 | 0 | 0 | 0 | 0 | 0
5F | 5F.3.2 | Precast Prestressed Concrete Structural Members, Class D (50 Mpa) | Cubic Meter | 500 | 8268.59 | 4134295 | 0 | 0 | 0 | 0 | 0
5F | 5F.4.1 | Bearing Devices, Pot, Fixed, 700 Ton | Unit | 3 | 42043.6 | 126130.8 | 0 | 0 | 0 | 0 | 0
5F | 5F.4.2.1 | Bearing Devices, Pot, Sliding, 400 Ton | Unit | 6 | 35764.16 | 214584.96 | 0 | 0 | 0 | 0 | 0
5F | 5F.4.2.2 | Bearing Devices, Pot, Sliding, 700 Ton | Unit | 3 | 42043.6 | 126130.8 | 0 | 0 | 0 | 0 | 0
5F | 5F.5.1 | Bearing Devices, Pot, Guided, 400 Ton | Unit | 6 | 42043.6 | 252261.6 | 0 | 0 | 0 | 0 | 0
5F | 5F.5.2 | Bearing Devices, Pot, Guided, 700 Ton | Unit | 6 | 49579.67 | 297478.02 | 0 | 0 | 0 | 0 | 0
5F | 5F.6 | Prestressing Steel | Ton | 26 | 26212.72 | 681530.72 | 0 | 0 | 0 | 0 | 0
5F | 5F.7.1 | Expansion Joints, Less than 50mm with Backing rod and sealant | Linear Meter | 20 | 170.86 | 3417.2 | 0 | 0 | 0 | 0 | 0
5F | 5F.7.2 | Expansion Joints, greater than 70 mm | Linear Meter | 40 | 8759.62 | 350384.8 | 0 | 0 | 0 | 0 | 0
5F | 5F.8.1 | Bridge single face parapet | Linear Meter | 670 | 1350.32 | 904714.4 | 0 | 0 | 0 | 0 | 0
5F | 5F.9 | Permeable Material behind Abutment with 300mm thick | Square Metre | 200 | 55.56 | 11112 | 0 | 0 | 0 | 0 | 0
5F | 5F.10 | Granular Backfill Behind Abutment | Cubic Metre | 470 | 104.66 | 49190.2 | 0 | 0 | 0 | 0 | 0
5F | 5F.11.1 | Bridge Deck Drainage System (150mm dia UPVC) | Linear Meter | 18 | 466.64 | 8399.52 | 0 | 0 | 0 | 0 | 0
5F | 5F.11.2 | Bridge Deck Drainage System (150mm dia Perforated PVC) | Linear Meter | 19 | 720.17 | 13683.23 | 0 | 0 | 0 | 0 | 0
5F | 5F.11.3 | Bridge Deck Drainage System - Flexible Drainage Pipe at Edge of Joint | Linear Meter | 15 | 341.71 | 5125.65 | 0 | 0 | 0 | 0 | 0
5F | 5F.11.4 | Bridge Deck Drainage System (75mm Dia PVC Pipe) | Linear Meter | 5 | 275.58 | 1240.11 | 0 | 0 | 0 | 0 | 0
5F | 5F.11.5 | Bridge Deck Drainage System (150mm dia Imperforated PVC) | Linear Meter | 39 | 846.93 | 33030.27 | 0 | 0 | 0 | 0 | 0
5F | 5F.12.1 | Waterproof Membrane, 2 Layers | Square Meter | 1800 | 155.15 | 279270 | 226.68 | 264.79 | 491.47 | 41082.1685 | 76251.5705
5F | 5F.12.2 | Waterproof Membrane For Bridge Deck (Pitchmastic) | Square Meter | 3300 | 179.95 | 593835 | 0 | 0 | 0 | 0 | 0
5F | 5F.12.3 | Polythene Membrane For Approach Slab, 2 Layers (150 micron) | Square Meter | 100 | 59.27 | 5927 | 0 | 0 | 0 | 0 | 0
5F | 5F.12.4 | Bituminous Painting for Buried Concrete | Square Meter | 700 | 81.31 | 56917 | 0 | 0 | 0 | 0 | 0
5F | 5F.13.1 | Protective Coating for Concrete Structure, Resistance to Weathering | Square Meter | 5800 | 143.96 | 834968 | 0 | 0 | 0 | 0 | 0
5F | 5F.14 | Reinforcing Steel, Grade 60 | Kilogram | 965000 | 5.68 | 5481200 | 25955 | 41617.3 | 67572.3 | 236386.264 | 383810.664
5F | 5F.15.1 | Structural Steel Supply, Fabrication, Finishing and Erection | Kilogram | 550000 | 32.44 | 17842000 | 0 | 0 | 0 | 0 | 0
5F | 5F.15.2 | Supply and Installation of Corrugated Steel Sheet | Square Meter | 1400 | 462.97 | 648158 | 0 | 0 | 0 | 0 | 0
5F | 5F.16.1 | Bituminous Concrete Wearing Course for Bridge Section, Depth 70mm | Square Meter | 2936 | 77.78 | 228323.19 | 0 | 0 | 0 | 0 | 0
7 | 7.1 | 12m lighting pole, 1 bracket, 1 LED luminaire 144W (Type L1) | Unit | 871 | 6151.06 | 5357573.26 | 0 | 0 | 0 | 0 | 0
7 | 7.2 | Reinforced Concrete Foundation for 12m Height Pole (Single Bracket) | Unit | 871 | 2103.98 | 1832566.58 | 0 | 0 | 0 | 0 | 0
7 | 7.3 | 12m lighting pole, 2 LED luminaire 144W (Type L2) | Unit | 577 | 10175.09 | 5871026.93 | 0 | 0 | 0 | 0 | 0
7 | 7.4 | Reinforced Concrete Foundation for 12m Height Pole (Double Bracket) | Unit | 577 | 2103.98 | 1213996.46 | 0 | 0 | 0 | 0 | 0
7 | 7.5 | 12m lighting pole, 1 LED 144W + 1 LED 24.3W (Type L5) | Unit | 47 | 6151.06 | 289099.82 | 0 | 0 | 0 | 0 | 0
7 | 7.6 | Reinforced Concrete Foundation for 12m Height Pole | Unit | 47 | 2103.98 | 98887.06 | 0 | 0 | 0 | 0 | 0
7 | 7.7 | Surface mounted linear LED luminaire 44.6W inside underpass (Type L4) | Unit | 345 | 1110.93 | 383270.85 | 0 | 0 | 0 | 0 | 0
7 | 7.8 | Surface mounted linear LED luminaire 110W under bridge deck (Type L3) | Unit | 42 | 1262.42 | 53021.64 | 0 | 0 | 0 | 0 | 0
7 | 7.9 | Road LED luminaire 21W at bridge/flyover areas (Type L6) | Unit | 1294 | 4410.4 | 5707057.6 | 0 | 0 | 0 | 0 | 0
7 | 7.10 | Surface mounted linear LED luminaire 25W in Pump Room | Unit | 18 | 1091.74 | 19651.32 | 0 | 0 | 0 | 0 | 0
7 | 7.11 | Surface mounted linear LED luminaire 25W with 90 min battery in Pump Room | Unit | 6 | 1428.37 | 8570.22 | 0 | 0 | 0 | 0 | 0
7 | 7.12 | RCC Concrete duct bank under road crossing (telecom) | Linear Meter | 31900 | 1079.98 | 34451362 | 0 | 0 | 0 | 0 | 0
7 | 7.13 | RCC duct bank (4x50mm) PVC duct, Telecom transverse under roads | Linear Meter | 5840 | 435.11 | 2541042.4 | 0 | 0 | 0 | 0 | 0
7 | 7.14 | RCC duct bank (2x110mm) HDPE duct, MOI cable longitudinal | Linear Meter | 14895 | 265.19 | 3950005.05 | 0 | 0 | 0 | 0 | 0
7 | 7.15 | RCC duct bank (4x110mm) HDPE duct, MONG cable longitudinal | Linear Meter | 15845 | 595.27 | 9432053.15 | 0 | 0 | 0 | 0 | 0
7 | 7.16 | RCC duct bank (4x100mm) PVC duct, Security camera cable longitudinal | Linear Meter | 15405 | 570.28 | 8785163.4 | 0 | 1483.58 | 1483.58 | 846056.0024 | 846056.0024
7 | 7.17 | RCC duct bank (4x100mm) PVC duct, Street Lighting Corridor longitudinal | Linear Meter | 54170 | 570.28 | 30892067.6 | 0 | 1566.7 | 1566.7 | 893457.676 | 893457.676
7 | 7.18 | RCC duct bank (6x150mm) PVC duct, MV cable longitudinal | Linear Meter | 31890 | 996.05 | 31764034.5 | 0 | 0 | 0 | 0 | 0
7 | 7.19 | RCC duct bank (8x100mm) PVC duct, LV cable longitudinal | Linear Meter | 32635 | 1088.42 | 35520586.7 | 0 | 0 | 0 | 0 | 0
7 | 7.20 | RCC duct bank (3x150mm) PVC duct, LV & MV transverse | Linear Meter | 9053 | 469.12 | 4246943.36 | 0 | 0 | 0 | 0 | 0
7 | 7.21 | RCC duct bank (4x150mm) PVC duct, Electrical Transfer cable longitudinal | Linear Meter | 31900 | 711.03 | 22681857 | 0 | 0 | 0 | 0 | 0
7 | 7.22 | Handhole/Manhole for Street Lighting & ITS Corridor 1.0x1.0x1.5m | Unit | 809 | 15220.66 | 12313513.94 | 0 | 0 | 0 | 0 | 0
7 | 7.23 | Manhole for Proposed Corridor (LV, MV & Telecom) 1.0x1.0x1.5m | Unit | 1308 | 15220.66 | 19908623.28 | 0 | 0 | 0 | 0 | 0
7 | 7.24 | Manhole for Proposed ET 1.5x1.5x1.5m | Unit | 223 | 19143.15 | 4268922.45 | 0 | 0 | 0 | 0 | 0
7 | 7.25 | Manhole for Proposed Corridor (MONG) two cover chamber | Unit | 44 | 22972.8 | 1010803.2 | 0 | 0 | 0 | 0 | 0
7 | 7.26 | Manhole for Proposed Corridor (MOI) 1.0x1.0x1.0m | Unit | 72 | 14770.41 | 1063469.52 | 0 | 0 | 0 | 0 | 0
7 | 7.27 | Manhole for Proposed Bridge 4.0x2.5x2.0m | Unit | 14 | 47344.68 | 662825.52 | 0 | 0 | 0 | 0 | 0
7 | 7.28 | Manhole for Proposed Bridge 3.0x2.5x2.0m | Unit | 6 | 50090.68 | 300544.08 | 0 | 0 | 0 | 0 | 0
7 | 7.29 | Manhole for Proposed Bridge 2.15x1.2x2.0m | Unit | 6 | 37216.65 | 223299.9 | 0 | 0 | 0 | 0 | 0
7 | 7.30 | Manhole for Proposed Bridge 7.5x2.5x2.0m | Unit | 2 | 78504.61 | 157009.22 | 0 | 0 | 0 | 0 | 0
7 | 7.31 | IP54 Outdoor unit substation 13.8kV, 500kVA | Unit | 1 | 557729.78 | 557729.78 | 0 | 0 | 0 | 0 | 0
7 | 7.32 | Reinforced concrete Base for Unit Sub-Stations | Unit | 1 | 4911.49 | 4911.49 | 0 | 0 | 0 | 0 | 0
7 | 7.33 | IP54 Outdoor unit substation 13.8kV, 1000kVA | Unit | 6 | 636644.14 | 3819864.84 | 0 | 0 | 0 | 0 | 0
7 | 7.34 | Reinforced concrete Base for Unit Sub-Stations | Unit | 6 | 7016.41 | 42098.46 | 0 | 0 | 0 | 0 | 0
7 | 7.35 | Street Lighting Panel supply, installation, testing, commissioning | Unit | 24 | 37871.98 | 908927.52 | 0 | 0 | 0 | 0 | 0
7 | 7.36 | Reinforced concrete Base for Feeder Pillars | Unit | 32 | 279.81 | 8953.92 | 0 | 0 | 0 | 0 | 0
7 | 7.37 | MCC (Motor Control Center) in Pump Room | Unit | 2 | 210399.81 | 420799.62 | 0 | 0 | 0 | 0 | 0
7 | 7.38 | Distribution Boards in Pump Room, IP54, 63A | Unit | 2 | 37871.98 | 75743.96 | 0 | 0 | 0 | 0 | 0
7 | 7.39 | Uninterrupted Power Supply 1kVA UPS | Unit | 2 | 12298.34 | 24596.68 | 0 | 0 | 0 | 0 | 0
7 | 7.40.1 | XLPE armoured cable 4Cx240+1Cx120 Sqmm CPC | Linear Meter | 4788 | 1241.21 | 5942913.48 | 0 | 0 | 0 | 0 | 0
7 | 7.40.2 | XLPE armoured cable 4Cx185+1Cx95 Sqmm CPC | Linear Meter | 2936 | 959.1 | 2815917.6 | 0 | 0 | 0 | 0 | 0
7 | 7.40.3 | XLPE armoured cable 4Cx150+1Cx95 Sqmm CPC | Linear Meter | 3452 | 794.52 | 2742683.04 | 0 | 0 | 0 | 0 | 0
7 | 7.40.4 | XLPE armoured cable 4Cx120+1Cx70 Sqmm CPC | Linear Meter | 1552 | 636.59 | 987987.68 | 0 | 0 | 0 | 0 | 0
7 | 7.40.5 | XLPE armoured cable 4Cx95+1Cx50 Sqmm CPC | Linear Meter | 4129 | 501.08 | 2068959.32 | 0 | 0 | 0 | 0 | 0
7 | 7.40.6 | XLPE armoured cable 4Cx70+1Cx35 Sqmm CPC | Linear Meter | 2474 | 365.17 | 903430.58 | 0 | 0 | 0 | 0 | 0
7 | 7.40.7 | XLPE armoured cable 4Cx50+1Cx25 Sqmm CPC | Linear Meter | 3873 | 257.08 | 995670.84 | 0 | 0 | 0 | 0 | 0
7 | 7.40.8 | XLPE armoured cable 4Cx35+1Cx16 Sqmm CPC | Linear Meter | 8108 | 189.99 | 1540438.92 | 0 | 0 | 0 | 0 | 0
7 | 7.40.9 | XLPE armoured cable 4Cx25+1Cx16 Sqmm CPC | Linear Meter | 5438 | 145.91 | 793458.58 | 0 | 0 | 0 | 0 | 0
7 | 7.40.10 | XLPE armoured cable 4Cx16+1Cx16 Sqmm CPC | Linear Meter | 16244 | 95.34 | 1548702.96 | 0 | 0 | 0 | 0 | 0
7 | 7.40.11 | XLPE armoured cable 4Cx300+1Cx150 Sqmm CPC | Linear Meter | 17609 | 278.07 | 4896534.63 | 0 | 0 | 0 | 0 | 0
7 | 7.40.12 | XLPE armoured cable 3Cx50+1Cx25 Sqmm CPC | Linear Meter | 27 | 209.22 | 5648.94 | 0 | 0 | 0 | 0 | 0
7 | 7.40.13 | XLPE armoured cable 3Cx16+1Cx16 Sqmm CPC | Linear Meter | 79 | 107.26 | 8473.54 | 0 | 0 | 0 | 0 | 0
7 | 7.40.14 | XLPE armoured cable 3Cx25+1Cx16 Sqmm CPC | Linear Meter | 53 | 83.42 | 4421.26 | 0 | 0 | 0 | 0 | 0
7 | 7.40.15 | XLPE armoured cable 3Cx10+1Cx10 Sqmm CPC | Linear Meter | 53 | 39.72 | 2105.16 | 0 | 0 | 0 | 0 | 0
7 | 7.40.16 | XLPE armoured cable 4Cx10+1Cx10 Sqmm CPC | Linear Meter | 62943 | 62.93 | 3961002.99 | 0 | 0 | 0 | 0 | 0
7 | 7.40.17 | Cable 2Cx2.5 Sqmm (CU/PVC)+1Cx2.5 Sqmm CPC | Linear Meter | 29014 | 9.27 | 268959.78 | 0 | 0 | 0 | 0 | 0
7 | 7.41.1 | Termination 4Cx240+1Cx120 Sqmm | Unit | 14 | 589.12 | 8247.68 | 0 | 0 | 0 | 0 | 0
7 | 7.41.2 | Termination 4Cx185+1Cx95 Sqmm | Unit | 14 | 589.12 | 8247.68 | 0 | 0 | 0 | 0 | 0
7 | 7.41.3 | Termination 4Cx150+1Cx95 Sqmm | Unit | 6 | 589.12 | 3534.72 | 0 | 0 | 0 | 0 | 0
7 | 7.41.4 | Termination 4Cx120+1Cx70 Sqmm | Unit | 6 | 589.12 | 3534.72 | 0 | 0 | 0 | 0 | 0
7 | 7.41.5 | Termination 4Cx95+1Cx50 Sqmm | Unit | 20 | 420.81 | 8416.2 | 0 | 0 | 0 | 0 | 0
7 | 7.41.6 | Termination 4Cx70+1Cx35 Sqmm | Unit | 6 | 420.81 | 2524.86 | 0 | 0 | 0 | 0 | 0
7 | 7.41.7 | Termination 4Cx50+1Cx25 Sqmm | Unit | 16 | 378.74 | 6059.84 | 0 | 0 | 0 | 0 | 0
7 | 7.41.8 | Termination 4Cx35+1Cx16 Sqmm | Unit | 26 | 336.63 | 8752.38 | 0 | 0 | 0 | 0 | 0
7 | 7.41.9 | Termination 4Cx25+1Cx16 Sqmm | Unit | 18 | 252.49 | 4544.82 | 0 | 0 | 0 | 0 | 0
7 | 7.41.10 | Termination 4Cx16+1Cx16 Sqmm | Unit | 66 | 101.01 | 6666.66 | 0 | 0 | 0 | 0 | 0
7 | 7.41.11 | Termination 4Cx300+1Cx150 Sqmm | Unit | 22 | 240.86 | 5298.92 | 0 | 0 | 0 | 0 | 0
7 | 7.41.12 | Termination 3Cx50+1Cx25 Sqmm | Unit | 2 | 161.22 | 322.44 | 0 | 0 | 0 | 0 | 0
7 | 7.41.13 | Termination 3Cx16+1Cx16 Sqmm | Unit | 6 | 161.22 | 967.32 | 0 | 0 | 0 | 0 | 0
7 | 7.41.14 | Termination 3Cx25+1Cx16 Sqmm | Unit | 4 | 161.22 | 644.88 | 0 | 0 | 0 | 0 | 0
7 | 7.41.15 | Termination 3Cx10+1Cx10 Sqmm | Unit | 4 | 101.01 | 404.04 | 0 | 0 | 0 | 0 | 0
7 | 7.41.16 | Termination 4Cx10+1Cx10 Sqmm | Unit | 258 | 101.01 | 26060.58 | 0 | 0 | 0 | 0 | 0
7 | 7.41.17 | Termination 2Cx2.5+1Cx2.5 Sqmm | Unit | 92 | 101.01 | 9292.92 | 0 | 0 | 0 | 0 | 0
7 | 7.42.1 | Control cable 2C x2.5 Sqmm | Linear Meter | 100 | 6.91 | 691 | 0 | 0 | 0 | 0 | 0
7 | 7.42.2 | Control cable 2Cx1.5 Sqmm | Linear Meter | 100 | 4.94 | 494 | 0 | 0 | 0 | 0 | 0
7 | 7.42.3 | Control cable 3Cx1.5 Sqmm | Linear Meter | 100 | 6.48 | 648 | 0 | 0 | 0 | 0 | 0
7 | 7.42.4 | Control cable 3Cx2.5 Sqmm | Linear Meter | 100 | 9.4 | 940 | 0 | 0 | 0 | 0 | 0
7 | 7.42.5 | Control cable 3Cx4 Sqmm | Linear Meter | 100 | 14.21 | 1421 | 0 | 0 | 0 | 0 | 0
7 | 7.42.6 | Control cable 4Cx2.5 Sqmm | Linear Meter | 100 | 11.89 | 1189 | 0 | 0 | 0 | 0 | 0
7 | 7.42.7 | Control cable 6Cx2.5 Sqmm | Linear Meter | 100 | 17.86 | 1786 | 0 | 0 | 0 | 0 | 0
7 | 7.42.8 | Control cable 12Cx2.5 Sqmm | Linear Meter | 100 | 35.71 | 3571 | 0 | 0 | 0 | 0 | 0
7 | 7.42.9 | Control cable 24Cx2.5 Sqmm | Linear Meter | 100 | 71.43 | 7143 | 0 | 0 | 0 | 0 | 0
7 | 7.43 | 16mm Dia Cu Coated Steel earth rod 1.2m - Set | Unit | 250 | 491.93 | 122982.5 | 0 | 0 | 0 | 0 | 0
7 | 7.44 | Main Earth Terminal (50x6)mm 600mm Cu earthing bus | Unit | 2 | 262.36 | 524.72 | 0 | 0 | 0 | 0 | 0
7 | 7.45 | 900x100mm ladder galvanized steel cable trays (Section C & B tie) | Linear Meter | 1550 | 319.76 | 495628 | 0 | 0 | 0 | 0 | 0
7 | 7.46 | 600x100mm ladder galvanized steel cable trays (Pump Room) | Linear Meter | 30 | 213.17 | 6395.1 | 0 | 0 | 0 | 0 | 0
7 | 7.47 | 300x100mm ladder galvanized steel cable trays (Pump Room) | Linear Meter | 30 | 155.78 | 4673.4 | 0 | 0 | 0 | 0 | 0
7 | 7.48 | 600x100mm ladder galvanized steel cable trays (Bridge deck utility corridor) | Linear Meter | 22008 | 213.17 | 4691445.36 | 0 | 0 | 0 | 0 | 0
7 | 7.49 | Supply of CU strips 50x6mm for Earthing System (Pump Room) | Linear Meter | 250 | 328.77 | 82192.5 | 0 | 0 | 0 | 0 | 0
7 | 7.50 | 16A socket outlet IP65 with switch (Pump Room) | Unit | 6 | 1229.83 | 7378.98 | 0 | 0 | 0 | 0 | 0
7 | 7.51 | 6A modular switch with safety shutter (Pump Room) | Unit | 2 | 409.94 | 819.88 | 0 | 0 | 0 | 0 | 0
7 | 7.52.1.1 | 32-bits CPU module with 2 Ethernet ports + RS232 + RS485 | Unit | 2 | 20608.37 | 41216.74 | 0 | 0 | 0 | 0 | 0
7 | 7.52.1.2 | DC Power supply, 48 VDC and/or +24 VDC with battery charger | Unit | 2 | 7556.27 | 15112.54 | 0 | 0 | 0 | 0 | 0
7 | 7.52.1.3 | GSM/GPRS communication module | Unit | 2 | 48084.92 | 96169.84 | 0 | 0 | 0 | 0 | 0
7 | 7.52.1.4 | Hi gain +6 dB omnidirectional GSM antenna | Unit | 2 | 181350.57 | 362701.14 | 0 | 0 | 0 | 0 | 0
7 | 7.52.1.5 | 8 channel Analog Input module | Unit | 2 | 51877.68 | 103755.36 | 0 | 0 | 0 | 0 | 0
7 | 7.52.1.6 | 16 channel digital input module, 24/48V | Unit | 4 | 101450.7 | 405802.8 | 0 | 0 | 0 | 0 | 0
7 | 7.52.1.7 | 16 channel digital output module, 24/48V 350 mA | Unit | 2 | 101450.7 | 202901.4 | 0 | 0 | 0 | 0 | 0
7 | 7.52.1.8 | Rack 15 slots DIN rail mounting | Unit | 2 | 57643.14 | 115286.28 | 0 | 0 | 0 | 0 | 0
7 | 7.52.1.9 | Programming software provision for RTU | Unit | 2 | 518775.53 | 1037551.06 | 0 | 0 | 0 | 0 | 0
7 | 7.52.1.10 | 8 port managed industrial switch | Unit | 2 | 86461.53 | 172923.06 | 0 | 0 | 0 | 0 | 0
7 | 7.52.1.11 | Fiber Optic Patch cord | Linear Metre | 20 | 138.64 | 2772.8 | 0 | 0 | 0 | 0 | 0
7 | 7.52.1.12 | FO Dome Splice closure 6F-12F, IP68 | Unit | 2 | 1729.76 | 3459.52 | 0 | 0 | 0 | 0 | 0
7 | 7.52.1.13 | SS316 cabinet IP65 1000x400x1200 | Unit | 2 | 63406.05 | 126812.1 | 0 | 0 | 0 | 0 | 0
7 | 7.52.1.14 | Supply, laying and termination of Cat-6 cables | Linear Metre | 50 | 16.53 | 826.5 | 0 | 0 | 0 | 0 | 0
7 | 7.52.1.15 | Armoured Single mode 6 core Fibre optic cable | Linear Metre | 8700 | 76.31 | 663897 | 0 | 0 | 0 | 0 | 0
7 | 7.52.1.16 | Un armoured 4 Core x 1.5 sq mm ATC FRLS screened control cable | Linear Metre | 620 | 36.88 | 22865.6 | 0 | 0 | 0 | 0 | 0
7 | 7.53 | ITS Panel supply, installation, testing, commissioning | Unit | 8 | 137984.35 | 1103874.8 | 0 | 0 | 0 | 0 | 0
10 | 10.1.1.1 | Structure Catch basins 600mm x 600mm | Unit | 3238 | 7490.35 | 24253753.3 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.1 | Manhole 1200mm, Depth 1m to 1.5m | Unit | 3 | 12132.73 | 36398.19 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.2 | Manhole 1200mm, Depth 1.5m to 2.0m | Unit | 59 | 12838.63 | 757479.17 | 0.15 | 0 | 0.15 | 0 | 1925.7945
10 | 10.1.2.3 | Manhole 1200mm, Depth 2.0m to 2.5m | Unit | 90 | 14816.41 | 1333476.9 | 2.4 | 0 | 2.4 | 0 | 35559.384
10 | 10.1.2.4 | Manhole 1200mm, Depth 2.5m to 3.0m | Unit | 80 | 18333.17 | 1466653.6 | 3.8 | 0 | 3.8 | 0 | 69666.046
10 | 10.1.2.5 | Manhole 1200mm, Depth 3m to 3.5m | Unit | 92 | 19317.83 | 1777240.36 | 2.4 | 0 | 2.4 | 0 | 46362.792
10 | 10.1.2.6 | Manhole 1200mm, Depth 3.5m to 4m | Unit | 86 | 20848.33 | 1792956.38 | 0.7 | 0 | 0.7 | 0 | 14593.831
10 | 10.1.2.7 | Manhole 1200mm, Depth 4m to 4.5m | Unit | 67 | 22331.14 | 1496186.38 | 2.25 | 0 | 2.25 | 0 | 50245.065
10 | 10.1.2.8 | Manhole 1200mm, Depth 4.5m to 5m | Unit | 52 | 23462.05 | 1220026.6 | 0.5 | 0 | 0.5 | 0 | 11731.025
10 | 10.1.2.9 | Manhole 1200mm, Depth 5m to 5.5m | Unit | 44 | 24895.05 | 1095382.2 | 0.35 | 0 | 0.35 | 0 | 8713.2675
10 | 10.1.2.10 | Manhole 1200mm, Depth 5.5m to 6m | Unit | 29 | 26523.06 | 769168.74 | 2.1 | 0 | 2.1 | 0 | 55698.426
10 | 10.1.2.11 | Manhole 1200mm, Depth 6m to 6.5m | Unit | 16 | 27557.53 | 440920.48 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.12 | Manhole 1200mm, Depth 6.5m to 7m | Unit | 8 | 29116.65 | 232933.2 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.13 | Manhole 1200mm, Depth 7m to 7.5m | Unit | 2 | 30630.19 | 61260.38 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.14 | Manhole 1200mm, Depth 7.5m to 8m | Unit | 1 | 31848.02 | 31848.02 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.15 | Manhole 1200mm, Depth 8m to 8.5m | Unit | 1 | 33371.11 | 33371.11 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.16 | Manhole 1200mm, Depth 9m to 9.5m | Unit | 2 | 36033.59 | 72067.18 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.17 | Manhole 1200mm, Depth 9.5m to 10m | Unit | 4 | 37780.31 | 151121.24 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.18 | Manhole 1200mm, Depth 10m to 10.5m | Unit | 1 | 39358.51 | 39358.51 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.19 | Manhole 1500mm, Depth 1.5m to 2.0m | Unit | 4 | 31797.15 | 127188.6 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.20 | Manhole 1500mm, Depth 2.0m to 2.5m | Unit | 16 | 34044.14 | 544706.24 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.21 | Manhole 1500mm, Depth 2.5m to 3.0m | Unit | 27 | 37971.09 | 1025219.43 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.22 | Manhole 1500mm, Depth 3m to 3.5m | Unit | 27 | 41496.34 | 1120401.18 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.23 | Manhole 1500mm, Depth 3.5m to 4m | Unit | 17 | 44163.06 | 750772.02 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.24 | Manhole 1500mm, Depth 4m to 4.5m | Unit | 22 | 47687.24 | 1049119.28 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.25 | Manhole 1500mm, Depth 4.5m to 5m | Unit | 32 | 51211.42 | 1638765.44 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.26 | Manhole 1500mm, Depth 5m to 5.5m | Unit | 18 | 53459.48 | 962270.64 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.27 | Manhole 1500mm, Depth 5.5m to 6m | Unit | 14 | 56983.67 | 797771.38 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.28 | Manhole 1500mm, Depth 6m to 6.5m | Unit | 5 | 61242.36 | 306211.8 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.29 | Manhole 1500mm, Depth 6.5m to 7m | Unit | 6 | 64767.61 | 388605.66 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.30 | Manhole 1500mm, Depth 7m to 7.5m | Unit | 2 | 67013.55 | 134027.1 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.31 | Manhole 1500mm, Depth 7.5m to 8m | Unit | 2 | 70958.51 | 141917.02 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.32 | Manhole 1500mm, Depth 8m to 8.5m | Unit | 1 | 74902.42 | 74902.42 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.33 | Manhole 1500mm, Depth 8.5m to 9m | Unit | 1 | 77150.48 | 77150.48 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.34 | Manhole 1500mm, Depth 9m to 9.5m | Unit | 1 | 81094.38 | 81094.38 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.35 | Manhole 1500mm, Depth 9.5m to 10m | Unit | 1 | 82922.72 | 82922.72 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.36 | Manhole 2000mm, Depth 2.5m to 3.0m | Unit | 9 | 45640.56 | 410765.04 | 0.08 | 0 | 0.08 | 0 | 3651.2448
10 | 10.1.2.37 | Manhole 2000mm, Depth 3m to 3.5m | Unit | 13 | 50166.36 | 652162.68 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.38 | Manhole 2000mm, Depth 3.5m to 4m | Unit | 15 | 52294.65 | 784419.75 | 0.15 | 0 | 0.15 | 0 | 7844.1975
10 | 10.1.2.39 | Manhole 2000mm, Depth 4m to 4.5m | Unit | 23 | 56820.44 | 1306870.12 | 1.4 | 0 | 1.4 | 0 | 79548.616
10 | 10.1.2.40 | Manhole 2000mm, Depth 4.5m to 5m | Unit | 28 | 61346.23 | 1717694.44 | 0.5 | 0 | 0.5 | 0 | 30673.115
10 | 10.1.2.41 | Manhole 2000mm, Depth 5m to 5.5m | Unit | 22 | 63949.36 | 1406885.92 | 0.3 | 0 | 0.3 | 0 | 19184.808
10 | 10.1.2.42 | Manhole 2000mm, Depth 5.5m to 6m | Unit | 20 | 68001.38 | 1360027.6 | 0.6 | 0 | 0.6 | 0 | 40800.828
10 | 10.1.2.43 | Manhole 2000mm, Depth 6m to 6.5m | Unit | 15 | 72527.17 | 1087907.55 | 0.15 | 0 | 0.15 | 0 | 10879.0755
10 | 10.1.2.44 | Manhole 2000mm, Depth 6.5m to 7m | Unit | 17 | 75130.3 | 1277215.1 | 0.15 | 0 | 0.15 | 0 | 11269.545
10 | 10.1.2.45 | Manhole 2000mm, Depth 7m to 7.5m | Unit | 14 | 79181.25 | 1108537.5 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.46 | Manhole 2000mm, Depth 7.5m to 8.0m | Unit | 6 | 81784.38 | 490706.28 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.47 | Manhole 2000mm, Depth 8m to 8.5m | Unit | 4 | 86310.17 | 345240.68 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.48 | Manhole 2000mm, Depth 8.5m to 9m | Unit | 1 | 90838.09 | 90838.09 | 0 | 0 | 0 | 0 | 0
10 | 10.1.2.49 | Manhole 2000mm, Depth 9m to 9.5m | Unit | 1 | 94887.98 | 94887.98 | 0 | 0 | 0 | 0 | 0
10 | 10.1.3 | Catchpit (2m x 1m) at Underpass of Depth Upto 1.5m | Unit | 2 | 13233.97 | 26467.94 | 0 | 0 | 0 | 0 | 0
10 | 10.1.4.1 | 1600x1200 RCC Rectangular Shaft, Depth 3.5m to 4m | Unit | 4 | 38101.46 | 152405.84 | 0 | 0.6 | 0.6 | 22860.876 | 22860.876
10 | 10.1.4.2 | 1600x1200 RCC Rectangular Shaft, Depth 4m to 4.5m | Unit | 2 | 34939.76 | 69879.52 | 0 | 0.4 | 0.4 | 13975.904 | 13975.904
10 | 10.1.4.3 | 1600x1200 RCC Rectangular Shaft, Depth 4.5m to 5m | Unit | 1 | 37331.97 | 37331.97 | 0 | 0.2 | 0.2 | 7466.394 | 7466.394
10 | 10.1.4.4 | 1600x1200 RCC Rectangular Shaft, Depth 5m to 5.5m | Unit | 1 | 40157.68 | 40157.68 | 0 | 0.2 | 0.2 | 8031.536 | 8031.536
10 | 10.1.4.5 | 1800x1200 RCC Rectangular Shaft, Depth 3m to 3.5m | Unit | 4 | 30457.43 | 121829.72 | 0 | 0 | 0 | 0 | 0
10 | 10.1.4.6 | 1800x1200 RCC Rectangular Shaft, Depth 3.5m to 4m | Unit | 4 | 33516.31 | 134065.24 | 0 | 0 | 0 | 0 | 0
10 | 10.1.4.7 | 1800x1200 RCC Rectangular Shaft, Depth 4m to 4.5m | Unit | 6 | 36865.61 | 221193.66 | 0 | 0 | 0 | 0 | 0
10 | 10.1.4.8 | 1800x1200 RCC Rectangular Shaft, Depth 4.5m to 5m | Unit | 4 | 39322.47 | 157289.88 | 0 | 0 | 0 | 0 | 0
10 | 10.1.4.9 | 1800x1200 RCC Rectangular Shaft, Depth 5m to 5.5m | Unit | 5 | 42301.86 | 211509.3 | 0 | 0 | 0 | 0 | 0
10 | 10.1.4.10 | 1800x1200 RCC Rectangular Shaft, Depth 5.5m to 6m | Unit | 2 | 45572.73 | 91145.46 | 0 | 0 | 0 | 0 | 0
10 | 10.1.4.11 | 1800x1200 RCC Rectangular Shaft, Depth 6m to 6.5m | Unit | 3 | 48843.6 | 146530.8 | 0 | 0 | 0 | 0 | 0
10 | 10.1.4.12 | 1800x1200 RCC Rectangular Shaft, Depth 6.5m to 7m | Unit | 4 | 51822.99 | 207291.96 | 0 | 0 | 0 | 0 | 0
10 | 10.1.4.13 | 1800x1200 RCC Rectangular Shaft, Depth 7m to 7.5m | Unit | 4 | 55093.86 | 220375.44 | 0 | 0 | 0 | 0 | 0
10 | 10.1.4.15 | 2000x1200 RCC Rectangular Shaft, Depth 4m to 4.5m | Unit | 1 | 37908.56 | 37908.56 | 0 | 0 | 0 | 0 | 0
10 | 10.1.4.16 | 2000x1200 RCC Rectangular Shaft, Depth 4.5m to 5m | Unit | 1 | 41333.11 | 41333.11 | 0 | 0 | 0 | 0 | 0
10 | 10.1.4.17 | 2000x1200 RCC Rectangular Shaft, Depth 5m to 5.5m | Unit | 5 | 44465.13 | 222325.65 | 0 | 0 | 0 | 0 | 0
10 | 10.1.4.18 | 2000x1200 RCC Rectangular Shaft, Depth 5.5m to 6m | Unit | 2 | 47890.74 | 95781.48 | 0 | 0 | 0 | 0 | 0
10 | 10.1.4.19 | 2000x1200 RCC Rectangular Shaft, Depth 6m to 6.5m | Unit | 2 | 51315.3 | 102630.6 | 0 | 0 | 0 | 0 | 0
10 | 10.1.4.20 | 2500x1200 RCC Rectangular Shaft, Depth 4.5m to 5m | Unit | 2 | 46359.18 | 92718.36 | 0 | 0 | 0 | 0 | 0
10 | 10.1.4.21 | 2500x1200 RCC Rectangular Shaft, Depth 5m to 5.5m | Unit | 1 | 49875.94 | 49875.94 | 0 | 0 | 0 | 0 | 0
10 | 10.1.4.22 | 2500x1200 RCC Rectangular Shaft, Depth 6.5m to 7m | Unit | 1 | 61010.25 | 61010.25 | 0 | 0 | 0 | 0 | 0
10 | 10.2.1 | 1600mm x 1600mm RCC Precast Box Conduit | Linear Metre | 408 | 3510.4 | 1432243.2 | 126 | 101.18 | 227.18 | 355182.272 | 797492.672
10 | 10.2.2 | 1800mm x 1800mm RCC Precast Box Conduit | Linear Metre | 626 | 4219.48 | 2641394.48 | 0 | 0 | 0 | 0 | 0
10 | 10.2.3 | 2000mm x 2000mm RCC Precast Box Conduit (printed as 10.2.2) | Linear Metre | 597 | 5001.69 | 2986008.93 | 0 | 0 | 0 | 0 | 0
10 | 10.2.4 | 1800mm x 1400mm RCC Precast Box Conduit | Linear Metre | 1150 | 5001.69 | 5750442.99 | 0 | 0 | 0 | 0 | 0
10 | 10.2.5 | 2500mm x 2500mm RCC Precast Box Conduit | Linear Metre | 154 | 7278.37 | 1120868.98 | 0 | 0 | 0 | 0 | 0
10 | 10.3.1 | GRP Storm Sewer Pipe, 300 mm dia | Linear Meter | 44904 | 381.9 | 17148837.6 | 1699.2 | 1603.2 | 3302.4 | 612262.08 | 1261186.56
10 | 10.3.2 | GRP Storm Sewer Pipe, 400 mm dia | Linear Meter | 16640 | 508.33 | 8458560.37 | 1015.78 | 64.19 | 1079.97 | 32629.7027 | 548981.1501
10 | 10.3.3 | GRP Storm Sewer Pipe, 500 mm dia | Linear Meter | 3182 | 611.8 | 1946931.14 | 392.35 | 4.9 | 397.25 | 2997.82 | 243037.55
10 | 10.3.4 | GRP Storm Sewer Pipe, 600 mm dia | Linear Meter | 3894 | 720.15 | 2804264.1 | 182.03 | 0 | 182.03 | 0 | 131088.9045
10 | 10.3.5 | GRP Storm Sewer Pipe, 700 mm dia | Linear Meter | 3459 | 848.3 | 2934269.7 | 14.4 | 0 | 14.4 | 0 | 12215.52
10 | 10.3.6 | GRP Storm Sewer Pipe, 800 mm dia | Linear Meter | 2864 | 998.28 | 2859373.4 | 0 | 43.2 | 43.2 | 43125.696 | 43125.696
10 | 10.3.7 | GRP Storm Sewer Pipe, 900 mm dia | Linear Meter | 2604 | 1156.88 | 3012978.27 | 136 | 0 | 136 | 0 | 157335.68
10 | 10.3.8 | GRP Storm Sewer Pipe, 1000 mm dia | Linear Meter | 2543 | 1337.25 | 3400626.75 | 142.8 | 9.64 | 152.44 | 12891.09 | 203850.39
10 | 10.3.9 | GRP Storm Sewer Pipe, 1200 mm dia | Linear Meter | 4244 | 1705.14 | 7236443.65 | 541.54 | 217.01 | 758.55 | 370032.4314 | 1293433.947
10 | 10.3.10 | GRP Storm Sewer Pipe, 1400 mm dia | Linear Meter | 1408 | 2276.86 | 3206046.57 | 177.62 | 19.28 | 196.9 | 43897.8608 | 448313.734
10 | 10.3.11 | GRP Storm Sewer Pipe, 1600 mm dia | Linear Meter | 917 | 2799.26 | 2567761.2 | 19.2 | 12.27 | 31.47 | 34346.9202 | 88092.7122
10 | 10.4 | Geotextile for StormWater Drainage mainline, Type II Fabric 250 g/m2 | Square Meter | 182067 | 15.9 | 2894872.11 | 8257.82 | 2753.29 | 11011.11 | 43777.311 | 175076.649
10 | 10.5 | Supply and Installation of Saucer drain including Concrete Base | Linear Metre | 950 | 127.19 | 120830.5 | 0 | 0 | 0 | 0 | 0
10 | 10.6.1.1 | HDPE Irrigation Pipe PN10, 50 mm dia | Linear Meter | 5854 | 53.7 | 314359.8 | 0 | 0 | 0 | 0 | 0
10 | 10.6.1.2 | HDPE Irrigation Pipe PN10, 63 mm dia | Linear Meter | 1569 | 59.07 | 92680.83 | 0 | 0 | 0 | 0 | 0
10 | 10.6.1.3 | HDPE Irrigation Pipe PN10, 75 mm dia | Linear Meter | 1446 | 96.66 | 139770.36 | 0 | 0 | 0 | 0 | 0
10 | 10.6.1.4 | HDPE Irrigation Pipe PN10, 90 mm dia | Linear Meter | 3642 | 132.91 | 484058.22 | 0 | 0 | 0 | 0 | 0
10 | 10.6.1.5 | HDPE Irrigation Pipe PN10, 110 mm dia | Linear Meter | 2882 | 167.82 | 483657.24 | 0 | 0 | 0 | 0 | 0
10 | 10.6.1.6 | HDPE Irrigation Pipe PN10, 125 mm dia | Linear Meter | 1810 | 181.24 | 328044.4 | 0 | 0 | 0 | 0 | 0
10 | 10.6.1.7 | HDPE Irrigation Pipe PN10, 140 mm dia | Linear Meter | 692 | 575.95 | 398557.4 | 0 | 0 | 0 | 0 | 0
10 | 10.6.1.8 | HDPE Irrigation Pipe PN10, 180 mm dia | Linear Meter | 49 | 275.22 | 13485.78 | 0 | 0 | 0 | 0 | 0
10 | 10.6.1.9 | HDPE Irrigation Pipe PN10, 200 mm dia | Linear Meter | 38 | 315.5 | 11989 | 0 | 0 | 0 | 0 | 0
10 | 10.6.1.10 | HDPE Irrigation Pipe PN10, 225 mm dia | Linear Meter | 2452 | 369.2 | 905278.4 | 0 | 0 | 0 | 0 | 0
10 | 10.6.1.11 | HDPE Irrigation Pipe PN10, 250 mm dia | Linear Meter | 1158 | 396.05 | 458625.9 | 0 | 0 | 0 | 0 | 0
10 | 10.6.2.1 | HDPE Irrigation Pipe PN16, 50 mm dia | Linear Meter | 6167 | 56.53 | 348620.51 | 0 | 0 | 0 | 0 | 0
10 | 10.6.2.2 | HDPE Irrigation Pipe PN16, 63 mm dia | Linear Meter | 3678 | 61.9 | 227668.2 | 0 | 0 | 0 | 0 | 0
10 | 10.6.2.3 | HDPE Irrigation Pipe PN16, 75 mm dia | Linear Meter | 3341 | 99.49 | 332396.09 | 0 | 0 | 0 | 0 | 0
10 | 10.6.2.4 | HDPE Irrigation Pipe PN16, 90 mm dia | Linear Meter | 1528 | 135.74 | 207410.72 | 0 | 0 | 0 | 0 | 0
10 | 10.6.2.5 | HDPE Irrigation Pipe PN16, 110 mm dia | Linear Meter | 977 | 170.64 | 166715.28 | 0 | 0 | 0 | 0 | 0
10 | 10.6.2.6 | HDPE Irrigation Pipe PN16, 125 mm dia | Linear Meter | 1836 | 184.07 | 337952.52 | 0 | 0 | 0 | 0 | 0
10 | 10.6.2.7 | HDPE Irrigation Pipe PN16, 140 mm dia | Linear Meter | 1934 | 237.77 | 459847.18 | 0 | 0 | 0 | 0 | 0
10 | 10.6.2.8 | HDPE Irrigation Pipe PN16, 180 mm dia | Linear Meter | 153 | 278.05 | 42541.65 | 0 | 0 | 0 | 0 | 0
10 | 10.6.2.9 | HDPE Irrigation Pipe PN16, 225 mm dia | Linear Meter | 1739 | 372.03 | 646960.17 | 0 | 0 | 0 | 0 | 0
10 | 10.6.2.10 | HDPE Irrigation Pipe PN16, 250 mm dia | Linear Meter | 1589 | 398.88 | 633820.32 | 0 | 0 | 0 | 0 | 0
10 | 10.7.1.1 | Air Valve Type II- 50 mm | Unit | 3 | 4967.42 | 14902.26 | 0 | 0 | 0 | 0 | 0
10 | 10.7.1.1(2) | Air Valve Type II- 63 mm (item no. printed as 10.7.1.1) | Unit | 1 | 5235.93 | 5235.93 | 0 | 0 | 0 | 0 | 0
10 | 10.7.1.2 | Air Valve Type II- 75 mm | Unit | 3 | 5772.95 | 17318.85 | 0 | 0 | 0 | 0 | 0
10 | 10.7.1.3 | Air Valve Type II- 90 mm | Unit | 3 | 6175.71 | 18527.13 | 0 | 0 | 0 | 0 | 0
10 | 10.7.1.4 | Air Valve Type II- 110 mm | Unit | 4 | 6578.48 | 26313.92 | 0 | 0 | 0 | 0 | 0
10 | 10.7.1.5 | Air Valve Type II- 125 mm | Unit | 1 | 6981.24 | 6981.24 | 0 | 0 | 0 | 0 | 0
10 | 10.7.1.6 | Air Valve Type II- 140 mm | Unit | 1 | 7249.75 | 7249.75 | 0 | 0 | 0 | 0 | 0
10 | 10.7.1.7 | Air Valve Type II- 180 mm | Unit | 1 | 7921.02 | 7921.02 | 0 | 0 | 0 | 0 | 0
10 | 10.7.1.8 | Air Valve Type II- 225 mm | Unit | 2 | 8726.55 | 17453.1 | 0 | 0 | 0 | 0 | 0
10 | 10.7.1.9 | Air Valve Type II- 250 mm | Unit | 2 | 9397.82 | 18795.64 | 0 | 0 | 0 | 0 | 0
10 | 10.7.2.1 | Valve, Gate, 50 mm | Unit | 7 | 3826.26 | 26783.82 | 0 | 0 | 0 | 0 | 0
10 | 10.7.2.2 | Valve, Gate, 63 mm | Unit | 8 | 4296.15 | 34369.2 | 0 | 0 | 0 | 0 | 0
10 | 10.7.2.3 | Valve, Gate, 75 mm | Unit | 8 | 4564.66 | 36517.28 | 0 | 0 | 0 | 0 | 0
10 | 10.7.2.4 | Valve, Gate, 90 mm | Unit | 14 | 5101.68 | 71423.52 | 0 | 0 | 0 | 0 | 0
10 | 10.7.2.5 | Valve, Gate, 110 mm | Unit | 4 | 5638.69 | 22554.76 | 0 | 0 | 0 | 0 | 0
10 | 10.7.2.6 | Valve, Gate, 125 mm | Unit | 5 | 5907.2 | 29536 | 0 | 0 | 0 | 0 | 0
10 | 10.7.2.7 | Valve, Gate, 140 mm | Unit | 3 | 6309.97 | 18929.91 | 0 | 0 | 0 | 0 | 0
10 | 10.7.2.8 | Valve, Gate, 200 mm | Unit | 1 | 6712.73 | 6712.73 | 0 | 0 | 0 | 0 | 0
10 | 10.7.2.9 | Valve, Gate, 225 mm | Unit | 4 | 7115.49 | 28461.96 | 0 | 0 | 0 | 0 | 0
10 | 10.7.2.10 | Valve, Gate, 250 mm | Unit | 3 | 8055.28 | 24165.84 | 0 | 0 | 0 | 0 | 0
10 | 10.7.3.1 | Pressure Reducing Valve, 50 mm | Unit | 3 | 7384 | 22152 | 0 | 0 | 0 | 0 | 0
10 | 10.7.3.2 | Pressure Reducing Valve, 63 mm | Unit | 2 | 8323.79 | 16647.58 | 0 | 0 | 0 | 0 | 0
10 | 10.7.3.3 | Pressure Reducing Valve, 75 mm | Unit | 1 | 9397.82 | 9397.82 | 0 | 0 | 0 | 0 | 0
10 | 10.7.3.4 | Pressure Reducing Valve, 90 mm | Unit | 1 | 10337.61 | 10337.61 | 0 | 0 | 0 | 0 | 0
10 | 10.7.3.5 | Pressure Reducing Valve, 110 mm | Unit | 1 | 11948.66 | 11948.66 | 0 | 0 | 0 | 0 | 0
10 | 10.7.3.6 | Pressure Reducing Valve, 125 mm | Unit | 1 | 12619.93 | 12619.93 | 0 | 0 | 0 | 0 | 0
10 | 10.7.3.7 | Pressure Reducing Valve, 225 mm | Unit | 2 | 14096.73 | 28193.46 | 0 | 0 | 0 | 0 | 0
10 | 10.7.4.1 | Remote Control Valve (Solenoid), 180 mm | Unit | 1 | 22823.29 | 22823.29 | 0 | 0 | 0 | 0 | 0
10 | 10.7.4.2 | Remote Control Valve (Solenoid), 250 mm | Unit | 1 | 26179.65 | 26179.65 | 0 | 0 | 0 | 0 | 0
10 | 10.7.5.1 | Washout Valve, 80 mm | Unit | 18 | 4430.4 | 79747.2 | 0 | 0 | 0 | 0 | 0
10 | 10.7.5.1(2) | Washout Valve, 100 mm (item no. printed as 10.7.5.1) | Unit | 3 | 4967.42 | 14902.26 | 0 | 0 | 0 | 0 | 0
10 | 10.7.6.1 | Flow Valve, 50 mm | Unit | 1 | 3893.38 | 3893.38 | 0 | 0 | 0 | 0 | 0
10 | 10.7.6.2 | Flow Valve, 90 mm | Unit | 1 | 4430.4 | 4430.4 | 0 | 0 | 0 | 0 | 0
10 | 10.7.6.3 | Flow Valve, 110 mm | Unit | 1 | 4967.42 | 4967.42 | 0 | 0 | 0 | 0 | 0
10 | 10.7.6.4 | Flow Valve, 125 mm | Unit | 1 | 5235.93 | 5235.93 | 0 | 0 | 0 | 0 | 0
10 | 10.7.6.5 | Flow Valve, 140 mm | Unit | 1 | 5772.95 | 5772.95 | 0 | 0 | 0 | 0 | 0
10 | 10.7.6.6 | Flow Valve, 200 mm | Unit | 1 | 6578.48 | 6578.48 | 0 | 0 | 0 | 0 | 0
10 | 10.7.6.7 | Flow Valve, 250 mm | Unit | 1 | 7384 | 7384 | 0 | 0 | 0 | 0 | 0
10 | 10.8.1 | Horizontal Centrifugal pump 55.52 cum/hr, 40m Head | Unit | 1 | 9934.84 | 9934.84 | 0 | 0 | 0 | 0 | 0
10 | 10.8.2 | Horizontal Centrifugal pump 38.87 cum/hr, 40m Head | Unit | 1 | 8726.55 | 8726.55 | 0 | 0 | 0 | 0 | 0
10 | 10.8.3 | Horizontal Centrifugal pump 33.1 cum/hr, 40m Head | Unit | 1 | 8726.55 | 8726.55 | 0 | 0 | 0 | 0 | 0
10 | 10.8.4 | Horizontal Centrifugal pump 129.23 cum/hr, 50m Head | Unit | 1 | 14096.73 | 14096.73 | 0 | 0 | 0 | 0 | 0
10 | 10.8.5 | Horizontal Centrifugal pump 90.46 cum/hr, 50m Head | Unit | 1 | 11814.41 | 11814.41 | 0 | 0 | 0 | 0 | 0
10 | 10.8.6 | Horizontal Centrifugal pump 58.15 cum/hr, 50m Head | Unit | 1 | 9800.59 | 9800.59 | 0 | 0 | 0 | 0 | 0
10 | 10.8.7 | Submersible Drain pump 18.51 cum/hr, 10m Head | Unit | 1 | 74897.6 | 74897.6 | 0 | 0 | 0 | 0 | 0
10 | 10.8.8 | Submersible Drain pump 41.35 cum/hr, 15m Head | Unit | 1 | 50724.99 | 50724.99 | 0 | 0 | 0 | 0 | 0
10 | 10.9.1 | RCC Underground Irrigation Pumping Station with 670 KL Storage Tank | Unit | 1 | 1303768.76 | 1303768.76 | 0 | 0 | 0 | 0 | 0
10 | 10.9.2 | RCC Underground Irrigation Pumping Station with 1560 KL Storage Tank | Unit | 1 | 2467162.29 | 2467162.29 | 0 | 0 | 0 | 0 | 0
10 | 10.9.3 | RCC Underground Irrigation Pumping Station with 1000 KL Tank (Sec D connection) | Unit | 1 | 87169.23 | 87169.23 | 0 | 0 | 0 | 0 | 0
10 | 10.9.4 | Fertilizer Tank with Injector for 670KL Tank | Unit | 1 | 806377.05 | 806377.05 | 0 | 0 | 0 | 0 | 0
10 | 10.9.5 | Fertilizer Tank with Injector for 1560KL Tank | Unit | 1 | 1128927.31 | 1128927.31 | 0 | 0 | 0 | 0 | 0
10 | 10.9.6 | Pumping Station Chain link fence and gates (Zone 1) | Linear Metre | 180 | 310.55 | 55899 | 0 | 0 | 0 | 0 | 0
10 | 10.9.7 | Pumping Station Chain link fence and gates (Zone 2) | Linear Metre | 140 | 310.55 | 43477 | 0 | 0 | 0 | 0 | 0
10 | 10.10.1 | Reuse/reprofile existing 1800mm x 1400mm Box Conduit | Linear Metre | 339 | 3815.66 | 1293508.74 | 0 | 0 | 0 | 0 | 0
10 | 10.10.2 | Reuse/reprofile existing Shaft/Manhole for the Conduit | Unit | 4 | 10175.09 | 40700.36 | 0 | 0 | 0 | 0 | 0

## Baseline_Plan
Month | Planned Value (excl VAT) | Planned Cum Value | Planned Cum % | Paste monthly planned value from the P6 baseline (cost-loaded S-curve / spending plan).
2025-10-01 |  | 0 | 0% | Or: site → Import File → drop the baseline .xer → Export what's loaded.
2025-11-01 |  | 0 | 0% | Add or delete month rows as needed (dates = 1st of month).
2025-12-01 |  | 0 | 0%
2026-01-01 |  | 0 | 0%
2026-02-01 |  | 0 | 0%
2026-03-01 |  | 0 | 0%
2026-04-01 |  | 0 | 0%
2026-05-01 |  | 0 | 0%
2026-06-01 |  | 0 | 0%
2026-07-01 |  | 0 | 0%
2026-08-01 |  | 0 | 0%
2026-09-01 |  | 0 | 0%
2026-10-01 |  | 0 | 0%
2026-11-01 |  | 0 | 0%
2026-12-01 |  | 0 | 0%
2027-01-01 |  | 0 | 0%
2027-02-01 |  | 0 | 0%
2027-03-01 |  | 0 | 0%
2027-04-01 |  | 0 | 0%
2027-05-01 |  | 0 | 0%
2027-06-01 |  | 0 | 0%
2027-07-01 |  | 0 | 0%
2027-08-01 |  | 0 | 0%
2027-09-01 |  | 0 | 0%
2027-10-01 |  | 0 | 0%
2027-11-01 |  | 0 | 0%
2027-12-01 |  | 0 | 0%
2028-01-01 |  | 0 | 0%
2028-02-01 |  | 0 | 0%
2028-03-01 |  | 0 | 0%
2028-04-01 |  | 0 | 0%
2028-05-01 |  | 0 | 0%
2028-06-01 |  | 0 | 0%
2028-07-01 |  | 0 | 0%
2028-08-01 |  | 0 | 0%
2028-09-01 |  | 0 | 0%
2028-10-01 |  | 0 | 0%
2028-11-01 |  | 0 | 0%
2028-12-01 |  | 0 | 0%
2029-01-01 |  | 0 | 0%
2029-02-01 |  | 0 | 0%
2029-03-01 |  | 0 | 0%
2029-04-01 |  | 0 | 0%
2029-05-01 |  | 0 | 0%
2029-06-01 |  | 0 | 0%
2029-07-01 |  | 0 | 0%
2029-08-01 |  | 0 | 0%
2029-09-01 |  | 0 | 0%
2029-10-01 |  | 0 | 0%
2029-11-01 |  | 0 | 0%
2029-12-01 |  | 0 | 0%
2030-01-01 |  | 0 | 0%
2030-02-01 |  | 0 | 0%
2030-03-01 |  | 0 | 0%
2030-04-01 |  | 0 | 0%
2030-05-01 |  | 0 | 0%
2030-06-01 |  | 0 | 0%
2030-07-01 |  | 0 | 0%
2030-08-01 |  | 0 | 0%
2030-09-01 |  | 0 | 0%

## Performance
Data Date | Planned % | Actual % | Remarks | Physical progress from each P6 update (Planned % = baseline, Actual % = performance % complete).